## DELIVERABLES
Bid Form Cost Proposal-Schedule of Deliverables RFP-22-005
ACTIVITY
Component | Year 1 8/01/22 to 7/31/23 | MONTH / YEAR | COST
2 | Develop/customize Online Test Delivery System to be used by students and school administrators for the 2023 SAFTs | Aug-Nov 22 | 0
1 | Construct 2023 SAFT Forms drawing from bank of item sets developed by previous contractor | Aug-Sep 22 | 0
2 | Prepare Web-based Online NYSESLAT CBT Practice Tests for Grades 2-12 to be hosted on contractor's website | Aug-Oct 22 | 0
1 | Select Schools for 2023 SAFTs | Oct-Dec 22 | 0
1 | Conduct Forms Construction Meeting with NYSED staff for 2023 operational tests | Oct-Nov 22 | 0
1 | Conduct Final Operational Test Forms Construction with NYS educators for 2023 operational tests | Oct-Dec 22 | 0
1 | Prepare School Administrator's Manual for 2023 operational tests | Oct-Dec 22 | 0
3 | Provide an Online Ordering System for the 2023 operational tests | Oct-Dec 22 | 0
1 | Prepare and send notification to selected schools for 2023 SAFTs | Nov-Dec 22 | 0
1 | Prepare Final Editions of 2023 SAFT Forms | Nov-Dec 22 | 0
1 | Conduct Final Eyes Review of the 2023 SAFTs with NYS educators | Nov-Dec 22 | 0
1 | Prepare 2023 SAFT directions for administration and other administration materials | Nov-Dec 22 | 0
4 | Develop an Informational Parent Brochure on the CBT system in English and 12 other languages | Nov-Dec 22 | 0
3 | Process 2023 Field Test Enrollments and develop shipping manifests to be used to pick and pack printed materials needed for SAFTs | Nov 22-Jan 23 | 0
2 | Host Ongoing Web-based Online NYSESLAT CBT Practice Tests for Grades 2-12 on Contractor's Website | Nov 22-Jul 23 | 0
3 | Maintain customer service helpline for 2023 exam ordering, pre-administration, SAFT and operational test administration, and scoring | Nov 22-May 23 | 0
1 | Conduct Final Eyes Review with NYS educators for 2023 operational tests | 2022-12-22 | 0
2 | Conduct six in person regional and four virtual Training Sessions for teachers and administrators in how to administer the NYSESLAT SAFTs using the contractor's CBT platform | Dec 22-Jan 23 | 0
1 | Print and duplicate 2023 SAFTs and related materials predominantly for grades K and 1 and DFAs for grades K-12 | Dec 22-Jan 23 | 0
1 | Conduct 1 in-person and 1 webinar type turnkey session for scoring the 2023 operational speaking and writing tests | 2023-01-01 | 0
3 | Process 2023 NYSESLAT operational test orders and supplemental requests, and pick and pack printed materials | Jan-Mar 23 | 0
1 | Prepare final copies of the 2023 PBT operational forms | Jan-Feb 23 | 0
1 | Ship 2023 SAFTs and related materials predominantly for grades K and 1 and DFAs for K-12 | 2023-02-23 | 0
1 | Develop 2023 operational test scoring materials for Speaking and Writing | 2023-02-23 | 0
1 | Commission Passages and Items for future SAFTs | 2023-02-23 | 0
1 | Administer 2023 SAFTs | Feb-Mar 23 | 0
1 | Conduct Cognitive Labs for the purpose of content validation and evidence for peer review | Feb-Mar 23 | 0
3 | Print 2023 operational test forms and related materials | Feb-Mar 23 | 0
3 | Print and Reproduce 2023 operational test scoring materials for Speaking and Writing | 2023-03-01 | 0
3 | Print 2023 operational tests braille and large type editions | 2023-03-01 | 0
3 | Process returned 2023 SAFT materials and contact schools regarding outstanding materials | Mar-June 23 | 0
3 | Ship 2023 operational test Braille and Large Type Editions as requested by schools | Mar-May 23 | 0
3 | Ship 2023 operational test forms and related materials | Mar-May 23 | 0
5 | Prepare a CBT test administration system/platform for the NYSITELL levels III-VIII | Mar-May 23 | 0
5 | Prepare the CBT Scoring system that tabulates the student’s raw scores and provides the educator with the student’s raw score for each modality and overall proficiency level and scoring platform for use by schools in Local Scoring of the NYSITELL Speaking and Writing questions (Levels III-VIII) | Mar-June 23 | 0
5 | Prepare a guide for administering the NYSITELL with CBT and Directions for Administering CBT NYSITELL Speaking and Directions for Administering CBT NYSITELL L/R/W for NYSED to print and ship to schools. | Mar-June 23 | 0
3 | Ship 2023 operational test scoring materials for Speaking and Writing | Apr-May 23 | 0
4 | Develop NYSESLAT Interim Assessment | May-June 23 | 0
1 | Scaling/equating and psychometric analysis of 2023 operational tests | May-Jun 23 | 0
5 | Host an online on-demand Tutorial for training teachers to administer the CBT NYSITELL levels III-VIII | June-July 23 | 0
1 | Process raw score data file for 2023 operational tests by summing raw scores, inserting scaled scores and proficiency levels, and returning files to NYS' data warehouse | June-July 23 | 0
3 | Process returned 2023 operational tests and contact schools with outstanding materials | 2023-06-23 | 0
1 | Conduct Rangefinding with NYS educators for scoring 2023 Writing field tests | June-July 23 | 0
1 | Conduct Rangefinding with NYS educators for scoring 2023 Speaking field tests | June-July 23 | 0
1 | Deliver General Research File to NYSED for 2023 operational tests | June-July 23 | 0
1 | Develop Exemplars for scoring the 2023 SAFT open ended questions and submit them to NYSED for review and approval | 2023-07-23 | 0
1 | Score 2023 NYSESLAT SAFTS (MC items) | 2023-07-01 | 0
1 | Conduct Annual NYS Educator Review of the NYSESLAT program | 2023-07-01 | 0
5 | Maintain CBT NYSITELL Helpline | 2023-07-23 | 0
5 | Provide a CBT Test Administration and Local Scoring System on an ongoing basis for the NYSITELL (Level III-VIII) | 2023-07-23 | 0
| TOTAL YEAR 1 |  | 0
Year 2 8/01/23 to 7/31/24
1 | Conduct Passage and Item review meeting with NYS educators for future SAFTs | 2023-08-23 | 0
1 | Score 2023 NYSESLAT SAFTS (CR items) | 2023-08-01 | 0
5 | Host an online on-demand Tutorial for training teachers to administer the CBT NYSITELL | Aug 23-July 24 | 0
5 | Maintain CBT NYSITELL Helpline | Aug 23-July 24 | 0
5 | Provide a CBT test administration and local scoring system on an ongoing basis for the NYSITELL (Level III-VIII) | Aug 23-July 24 | 0
5 | Provide to NYSED (OSA) Data Records of the Student Responses to the MC Items and Locally- Determined Scores for the Student Constructed Responses for the NYSITELL on a monthly basis | Aug 23-July 24 | 0
5 | Provide to NYSED’s State Repository Data Records of the Student’s date of administration of the NYSITELL and performance level results on a quarterly basis | Aug 23-July 24 | 0
4 | Submission of Form A interim assessment CBT and PBT (grades 2-12) to NYSED for its review | 2023-08-23 | 0
4 | Submission of Form A interim assessment PBT (grades K and 1) to NYSED for its review | 2023-08-24 | 0
2 | Host Ongoing Online CBT Practice Tests for Grades 2-12 on Contractor's Website with Sample Test Forms | Aug 23-July 24 | 0
1 | Conduct Rescoring of 10% of locally scored 2023 operational test writing responses | Aug-Sept 23 | 0
1 | Conduct Rescoring of 10% of locally scored 2023 operational test speaking responses | Aug-Sept 23 | 0
4 | Prepare a CBT Test Administration System/Platform for the interim assessement Form A (Grades 2-12) | Aug-Sept 23 | 0
4 | Prepare the CBT Scoring System that tabulates the student’s raw scores and provides the educator with the student’s raw score for each modality and overall proficiency level and scoring platform for use by schools in Local Scoring of the interim assessement Form A | Aug-Sept 23 | 0
4 | Develop and provide to NYSED for its review Scoring Materials for local scoring of the interim assessment Speaking and Writing questions (All grades) | Aug-Sept 23 | 0
1 | Construct 2024 SAFT Forms | Sept-Oct 23 | 0
4 | Provide the Online Ordering System for the NYSESLAT interim assessment Form A | Sept-Nov 23 | 0
1 | Provide Technical Report on 2023 NYSESLAT SAFTs | Sept-23 | 0
1 | Provide Technical Report on 2023 operational tests | Sept-Oct 23 | 0
1 | Update the Informational Parent Brochure on the CBT system in English and 12 other languages | Sept-Oct 23 | 0
4 | Print and ship Form A Interim Assessment Grades K and 1, printed ancillary materials for all grade levels, and accommodated versions of Grades 2-12 to schools | Oct-Nov 23 | 0
1 | Conduct Forms Construction Meeting with NYSED staff for 2024 operational tests | Oct-Nov 23 | 0
1 | Select schools for 2024 SAFTs | Oct-Dec 23 | 0
1 | Provide NYSED with Updated School Administrator’s Manual (SAM) for CBT/PBT 2024 Operational Tests | Oct-Dec 23 | 0
1 | Conduct Final Operational Test Forms Construction for CBT/PBT with NYS educators for 2024 operational tests | Oct-Dec 23 | 0
3 | Provide an online ordering system for the 2024 operational tests | Oct-Dec 23 | 0
2 | Conduct six in person regional and four virtual Training Sessions for teachers and administrators in how to administer the NYSITELL and the NYSESLAT interim assessment, SAFTs, and operational tests using the CBT system | 2023-11-23 | 0
4 | Provide a CBT test administration system and local scoring system for the Interim Assessment | Nov 23-Feb 24 | 0
1 | Prepare Final Editions of 2024 SAFT forms | Nov-Dec 23 | 0
1 | Prepare and send notification to selected schools for 2024 SAFTs | Nov-Dec 23 | 0
3 | Process 2024 Field Test Enrollments and develop shipping manifests to be used to pick and pack printed materials needed for SAFTs | Nov 23-Jan 24 | 0
1 | Prepare 2024 SAFT directions for administration and other administration materials | Nov-Dec 23 | 0
1 | Conduct Final Eyes Review with NYS educators for 2024 SAFTs | Nov-Dec 23 | 0
4 | Maintain Customer Service Helpline for interim assessment | Nov 23-Feb 24 | 0
1 | Maintain customer service helpline for 2024 exam ordering, pre-administration, SAFT and operational test administration, and scoring | Nov 23-May 24 | 0
2 | Develop and maintain CBT Technology Readiness Verification Tools for NYS Schools | Nov 23-Jan 24 | 0
1 | Conduct Final Eyes Review with NYS educators for 2024 operational tests | 2023-12-01 | 0
3 | Print and duplicate 2024 SAFTs and related materials predominantly for grades K and 1 and DFAs for K-12 | Dec 23-Jan 24 | 0
3 | Process Return of Shipped Secure interim assessment printed materials | Dec 23 -Feb 24 | 0
1 | Prepare final copies of the 2024 CBT and PBT operational forms | Jan-Feb 24 | 0
3 | Ship 2024 SAFTs and related materials predominantly for grades K and 1 and DFAs for K-12 | Jan-Feb 24 | 0
3 | Process 2024 NYSESLAT operational test orders and supplemental requests, and pick and pack printed materials | Jan-Mar 24 | 0
2 | Maintain Online Test Delivery System to be Used by Students and School Administrators for the 2024 Field Tests and operational tests | Jan-June 24 | 0
1 | Develop 2024 operational test scoring materials for Speaking and Writing | 2024-02-24 | 0
1 | Commission Passages and Items for future SAFTs | 2024-02-23 | 0
1 | Administer 2024 SAFTs | Feb-Mar 24 | 0
1 & 3 | Prepare and Print/Reproduce 2024 Operational Test Large-Type and Braille forms | Feb-Mar 24 | 0
3 | Print 2024 operational test forms and related materials predominantly for grades K and 1, and DFAs for grades K-12 | Feb-Mar 24 | 0
3 | Process returned 2024 SAFT materials and contact schools with outstanding materials | Mar-Apr 24 | 0
3 | Ship 2024 operational test forms and related materials predominantly for grades K and 1, DFAs for K-12. large type and braillle forms | Mar-May 24 | 0
1 | Administer 2024 Operational NYSESLAT | Apr-May 24 | 0
1 | Score 2024 Operational Tests MC items | May-June 24 | 0
1 | Score 2024 Student Responses for operational tests Speaking and Writing items | June-July 24 | 0
1 | Scaling/equating and psychometric analysis of 2024 operational tests | May-June 24 | 0
4 | Develop NYSESLAT Form B interim assessment (All grades) | May-Jun 24 | 0
1 | Standard Setting for 2024 Operational tests Grades 1-2 | June-July 24 | 0
3 | Process returned 2024 operational tests and contact schools with outstanding materials | 2024-06-24 | 0
1 | Conduct Rangefinding with NYS educators for scoring 2024 Writing SAFTs | Jun-July 24 | 0
1 | Conduct Rangefinding with NYS educators for scoring 2024 Speaking SAFTs | Jun-July 24 | 0
1 | Develop Exemplars for scoring the 2024 SAFT open ended questions and submit them to NYSED for review and approval | Jun-July 24 | 0
1 | Deliver General Research file to NYSED for 2024 operational tests | Jun-July 24 | 0
1 | Combine raw score data files for students' 2024 CBT and PBT operational tests, sum raw scores, insert scaled scores and proficiency levels, and furnish scored file to NYS' data warehouse | 2024-07-24 | 0
1 | Score 2024 NYSESLAT SAFTs (MC items) | 2024-07-24 | 0
1 | Conduct Annual NYS Educator Review of the NYSESLAT program | 2024-07-24 | 0
| TOTAL YEAR 2 |  | 0
Year 3 8/01/24 to 10/31/25
1 | Conduct Passage and Item review meeting with NYS educators for 2025 NYSESLAT SAFTs | 2024-08-24 | 0
1 | Score 2024 NYSESLAT SAFTs (CR items) | 2024-08-24 | 0
5 | Host an online on-demand Tutorial for training teachers to administer the CBT NYSITELL (Levels III-VIII) | Aug 24-Oct 25 | 0
5 | Maintain CBT NYSITELL Helpline (Levels III-VIII) | Aug 24-Oct 25 | 0
5 | Provide a CBT test administration and local scoring system on an ongoing basis for the NYSITELL (Level III-VIII) | Aug 24-Oct 25 | 0
5 | Provide to NYSED (OSA) Data Records of the Student Responses to the MC Items and Locally- Determined Scores for the Student Constructed Responses for the NYSITELL on a monthly basis. | Aug 24-Oct 25 | 0
5 | Provide to NYSED’s State Repository Data Records of the Student’s date of NYSITELL administration and performance level results on a quarterly basis | Aug 24-Oct 25 | 0
4 | Submission of Form B interim assessment CBT and PBT (grades 2-12) to NYSED for its review | Aug 24 | 0
4 | Submission of Form B Interim Assessment PBT Grades K and 1 to NYSED for its review | Aug 24 | 0
4 | Prepare/Update CBT Test Administration System/Platform for the Interim Assessment Form B (Grades 2-12) | Aug-Sept 24 | 0
4 | Prepare the CBT Scoring system that tabulates the student’s raw scores and provides the educator with the student’s raw score for each modality and overall proficiency level and scoring platform for use by schools in Local Scoring of the Form B Interim Assessment | Aug-Sep 24 | 0
4 | Develop and provide to NYSED for its review scoring materials for local scoring of the Form B Interim Assessment Speaking and Writing questions (All grades) | Aug-Sep 24 | 0
1 | Construct 2025 SAFT Forms | Sept-Oct 24 | 0
2 | Host Ongoing Online CBT Practice Tests for Grades 2-12 on Contractor's Website with Sample Test Forms | Aug 24-Oct 25 | 0
4 | Host Ordering System for schools NYSESLAT Form B Interim Assessment | Sept-Nov 24 | 0
1 | Provide Technical Report on 2024 NYSESLAT SAFTs | Sept-24 | 0
1 | Provide Technical Report on 2024 operational tests | Sept-Oct 24 | 0
1 | Update the Informational Parent Brochure on the CBT system in English and 12 other languages | Sept-Oct 24 | 0
4 | Print and Ship the Form B Interim Assessment for Grades K and 1, printed ancillary materials for all grade levels, and accommodated versions of Form B Grades 2-12 to schools | Oct-Nov 24 | 0
1 | Conduct Forms Construction Meeting with NYSED staff for 2025 operational tests | Oct-Nov 24 | 0
1 | Select schools for 2025 SAFTs | Oct-Dec 24 | 0
1 | Provide NYSED with Updated School Administrator’s Manual (SAM) for CBT/PBT 2025 Operational Tests | Oct-Dec 24 | 0
1 | Conduct Final Operational Test Forms Construction for CBT/PBTwith NYS educators for 2025 operational tests | Oct-Dec 24 | 0
3 | Provide an online ordering system for the 2025 operational tests | Oct -Dec 24 | 0
2 | Conduct six in person regional and four virtual Training Sessions for teachers and administrators in how to administer the NYSITELL and the NYSESLAT interim assessment, SAFTs, and operational tests using the CBT system | 2024-11-24 | 0
4 | Provide a CBT test administration system and local scoring system for the interim assessment Form B (grades 2-12) | Nov 24 -Feb 25 | 0
1 | Prepare Final Editions of 2025 SAFTs Forms | Nov-Dec 24 | 0
1 | Prepare and send notification to selected schools for 2025 SAFTs | Nov-Dec 24 | 0
1 | Process 2025 Field Test Enrollments and develop shipping manifests to be used to pick and pack printed materials needed for SAFTs | Nov 24-Jan 25 | 0
1 | Prepare 2025 SAFTs directions for administration and other administration materials | Nov-Dec 24 | 0
1 | Conduct Final Eyes Review of the 2025 SAFTs with NYS educators | Nov-Dec 24 | 0
4 | Provide a CBT Test Administration System and Local Scoring System for the interim assessment | Nov 24-Feb 25 | 0
4 | Maintain customer service helpline for interim assessment | Nov 24-Feb 25 | 0
3 | Maintain customer service helpline for 2025 exam ordering, pre-administration, SAFT and operational test administration, and scoring | Nov 24-May 25 | 0
1 | Conduct Final Eyes Review with NYS educators for 2025 operational tests | 2024-12-01 | 0
2 | Maintain CBT Technology Readiness Verification Tools for NYS schools | Dec 24-Jan 25 | 0
3 | Print and duplicate 2025 SAFTs and related materials predominantly for grades K and 1 and DFAs for K-12 | Dec 24-Jan 25 | 0
4 | Process Return of Shipped Printed secure interim assessment materials | Dec 24-Feb 25 | 0
1 | Prepare final copies of the 2025 operational CBT and PBT test forms | Jan-Feb 25 | 0
1 | Ship 2025 SAFTs and related materials predominantly for grades K and 1 and DFAs for K-12 | Jan-Feb 25 | 0
3 | Process 2025 NYSESLAT operational test orders and supplemental requests, and pick and pack printed materials | Jan-Mar 25 | 0
2 | Maintain Online Test Delivery System to be Used by Students and School Administrators for the 2024 Field Tests and operational tests | Jan-Jun 25 | 0
1 | Commission Passages and Items for future SAFTs | 2025-02-25 | 0
1 | Develop 2025 operational test scoring materials for Speaking and Writing | 2025-02-25 | 0
1 | Prepare 2025 operational test large-type and braille forms | 2025-02-25 | 0
1 | Administer 2025 SAFTs | Feb-Mar 25 | 0
3 | Print 2025 operational test forms and related materials predominantly for grades K and 1, DFAs for K-12. large type and braillle forms | Feb-Mar 25 | 0
3 | Process returned 2025 SAFT materials and contact schools with outstanding materials | Mar-Apr 25 | 0
3 | Ship 2025 operational test forms and related materials predominantly for grades K and 1, DFAs for K-12. large type and braillle forms | Mar-May 25 | 0
1 | Administer 2025 Operational NYSESLAT CBT and PBT | Apr-May 25 | 0
1 | Score 2025 operational tests MC items | May-June 25 | 0
1 | Score 2025 student responses for operational tests Speaking and Writing items | 2025-06-01 | 0
1 | Scaling/equating and psychometric analysis of 2025 operational tests | Jun-July 25 | 0
1 | Deliver General Research File to NYSED for 2025 operational tests | Jun-July 25 | 0
3 | Process returned 2025 printed secure operational tests and contact schools with outstanding materials | 2025-06-01 | 0
1 | Conduct Rangefinding with NYS educators for scoring 2025 Writing SAFTs | June-July 25 | 0
1 | Conduct Rangefinding with NYS educators for scoring 2025 Speaking SAFTs | June-July 25 | 0
1 | Combine raw score data files for students' 2025 CBT and PBT operational tests, sum raw scores, insert scaled scores and proficiency levels, and furnish scored file to NYS' data warehouse | 2025-07-25 | 0
1 | Develop Exemplars for scoring the 2025 SAFT open ended questions and submit them to NYSED for review and approval | 2025-07-25 | 0
1 | Score 2025 NYSESLAT SAFTs (MC items) | 2025-07-25 | 0
1 | Conduct Annual NYS Educator Review of the NYSESLAT program | 2025-07-25 | 0
1 | Score 2025 NYSESLAT SAFTs (CR items) | 2025-08-25 | 0
1 | Conduct Passage and Item Review Meeting with NYS educators for 2026 NYSESLAT SAFTs | 2025-08-25 | 0
1 | Provide Technical Report for 2025 NYSESLAT SAFTs | 2025-09-25 | 0
1 | Provide Technical Report on 2025 operational tests | Sept-Oct 25 | 0
| TOTAL YEAR 3 |  | 0
| TOTAL OF ALL 3 YEARS |  | 0

## BUDGET SUMMARY
Budget Form –Cost Proposal
New York State Education Department
Request for Proposals 22-005
Elementary, Intermediate (Middle) Level, and High School New York State English as a Second Language Achievement Test (NYSESLAT)
Bidder Name:
YEAR 1 | YEAR 2 | YEAR 3 | GRAND TOTAL
0 | 0 | 0 | 0
The Financial Criteria portion of the RFP will be scored based upon the grand total cost.
Vendors should be prepared to show how they derived the amounts for each activity should they be subject to audit by NYSED or Office of the State Comptroller.
Vendor Signature: |  |  | Date:
Printed Name:
Company Name:
Company Address:

## SUBCONTRACTING
Request for Proposals 22-005
Elementary, Intermediate (Middle) Level, and High School New York State English as a Second Language Achievement Test (NYSESLAT)
Subcontracting Form
Bidder Name:
Name of Subcontractor | M/WBE* | Entity Type | Work Description | Year 1 Cost | Multi-Year Cost (including Year 1)
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
|  |  |  | Total Multi-Year Subcontracting Costs | 0
|  |  |  | Total Multi-Year Project Budget | 0
|  |  |  | Total Multi-Year Subcontracting Costs divided by Total Multi-Year Budget (%)** | #DIV/0!
*Indicate whether the subcontractor is a Minority or Women–Owned Business Enterprise.
Leave box blank if subcontractor is neither.
**Subcontracting is limited to thirty percent (30%) of the total contract budget.

## MWBE
Request for Proposals 22-005
Elementary, Intermediate (Middle) Level, and High School New York State English as a Second Language Achievement Test (NYSESLAT)
MWBE Purchases Form
Bidder Name:
Table 1: Minority Business Enterprise (MBE)
Name of Vendor | Type of Services or Supplies | Year 1 Cost | Multi-Year Cost (including Year 1)
|  | Total MBE Costs | 0
|  | Total Budget | 0
|  | Total MBE Costs divided by Total Budget (%) | #DIV/0!
Table 2: Women-Owned Business Enterprise (WBE)
Name of Vendor | Type of Services or Supplies | Year 1 Cost | Multi-Year Cost (including Year 1)
|  | Total WBE Costs | 0
|  | Total Budget | 0
|  | Total WBE Costs divided by Total Budget (%) | #DIV/0!