## Year 1
CONTRACT YEAR 1 8/1/23 to 7/31/24 | MONTH / YEAR | TOTAL COST
Conduct forms construction meeting with NYSED Staff at NYSED's office for 2024 operational tests | Oct-Nov 2023
Select schools for 2024 stand alone field tests | Oct-Nov 2023
Prepare directions for administration and school administrator's manual for 2024 operational tests | Oct-Dec 2023
Prepare 2024 stand alone field test forms with input from NYSED | 2023-11-01
Prepare and send notification to selected schools for 2024 stand alone field tests | Nov-Dec 2023
Process 2024 field test enrollments and develop and print packing lists (manifests) to pick and pack material | Nov-Dec 2023
Prepare 2024 field test directions for administration and other administration materials | Nov-Dec 2023
Conduct final eyes review with NYS educators for 2024 stand alone field tests | Nov-Dec 2023
Process 2024 operational test orders, supplemental requests, and other necessary materials | Nov 2023-Jan 2024
Maintain customer service helpline for 2024 exam ordering and pre-administration | Nov 2023-Apr 2024
Conduct final eyes review with NYS educators for 2024 operational tests | 2023-12-01
Print and duplicate all 2024 stand alone field tests and related materials | Dec 2023-Jan 2024
Record 1 webinar to train scoring trainers for scoring the 2024 operational speaking and writing tests | 2024-01-01
Prepare final copies of the 2024 operational test forms | Jan-Feb 2024
Ship 2024 stand alone field tests and related materials | Jan-Feb 2024
Develop 2024 operational test scoring materials for Speaking and Writing | 2024-02-01
Prepare 2024 operational test large-type and braille forms | 2024-02-01
Administer 2024 stand alone field tests | Feb-Mar 2024
Print 2024 operational test forms and related materials | Feb-Mar 2024
Print and Reproduce 2024 operational test scoring materials for Speaking and Writing | 2024-03-01
Print 2024 operational tests braille and large-type editions | Mar-Apr 2024
Process returned 2024 stand alone field test materials and contact schools with outstanding materials | Mar-Apr 2024
Commission passages and items for 2025 field tests | Mar-Apr 2024
Ship 2024 operational test forms and related materials | Mar-May 2024
Ship 2024 operational test braille and large-type editions as requested by schools | Mar-May 2024
Ship 2024 operational test scoring materials for Speaking and Writing | Apr-May 2024
Maintain customer service helpline for 2024 operational administration and scoring periods | Apr-June 2024
Process returned 2024 operational tests and contact schools with outstanding materials | Apr-June 2024
Receive raw score data file for 2024 operational tests, score multiple choice components, sum raw scores, insert scaled scores and proficiency levels, return file | May-June 2024
Scaling/equating and psychometric analysis of 2024 operational tests | May-June 2024
Conduct rangefinding with NYS educators for scoring 2024 Writing field tests | June-July 2024
Deliver general research file to NYSED for 2024 operational tests | June-July 2024
Conduct Passage and Item review meeting with NYS educators for 2024 stand alone field tests | June-July 2024
Conduct standard setting meeting to establish cut scores for new Grade 1 operational test | 2024-07-01
Score 2024 NYSESLAT field tests (MC and CR items) | 2024-07-01
TOTAL YEAR 1 |  | 0

## Year 2
CONTRACT YEAR 2 8/1/24 to 10/31/25 | MONTH / YEAR | TOTAL COST
Conduct rescoring of 10% of locally scored 2024 operational test writing responses | Aug-Sept 2024
Provide technical report on 2024 stand alone field tests | Sept-24
Conduct forms construction meeting with NYSED Staff at NYSED's office for 2025 operational tests | Oct-Nov 2024
Select schools for 2025 stand alone field tests | Oct-Nov 2024
Prepare directions for administration and school administrator's manual for 2025 operational tests | Oct-Dec 2024
Prepare 2025 stand alone field test forms with input from NYSED | 2024-11-01
Provide technical report on 2024 operational tests | Nov-Dec 2024
Prepare and send notification to selected schools for 2025 stand alone field tests | Nov-Dec 2024
Process 2025 field test enrollments and develop and print packing lists (manifests) to pick and pack material | Nov-Dec 2024
Prepare 2025 field test directions for administration and other administration materials | Nov-Dec 2024
Conduct final eyes review with NYS educators for 2025 stand alone field tests | Nov-Dec 2024
Process 2025 operational test orders, supplemental requests, and other necessary materials | Nov 2024-Jan 2025
Maintain customer service helpline for 2025 exam ordering and pre-administration | Nov 2024-Apr 2025
Conduct final eyes review with NYS educators for 2025 operational tests | 2024-12-01
Print and duplicate all 2025 stand alone field tests and related materials | Dec 2024-Jan 2025
Prepare final copies of the 2025 operational test forms | Jan-Feb 2025
Ship 2025 stand alone field tests and related materials | Jan-Feb 2025
Develop 2025 operational test scoring materials for Speaking and Writing | 2025-02-01
Prepare 2025 operational test large-type and braille forms | 2025-02-01
Administer 2025 stand alone field tests | Feb-Mar 2025
Print 2025 operational test forms and related materials | Feb-Mar 2025
Print and Reproduce 2025 operational test scoring materials for Speaking and Writing | 2025-03-01
Print 2025 operational tests braille and large-type editions | Mar-Apr 2025
Process returned 2025 stand alone field test materials and contact schools with outstanding materials | Mar-Apr 2025
Commission passages and items for 2026 field tests | Mar-Apr 2025
Ship 2025 operational test forms and related materials | Mar-May 2025
Ship 2025 operational test braille and large-type editions as requested by schools | Mar-May 2025
Ship 2025 operational test scoring materials for Speaking and Writing | Apr-May 2025
Maintain customer service helpline for 2025 operational administration and scoring periods | Apr-June 2025
Process returned 2025 operational tests and contact schools with outstanding materials | Apr-June 2025
Receive raw score data file for 2025 operational tests, score multiple choice components, sum raw scores, insert scaled scores and proficiency levels, return file | May-June 2025
Scaling/equating and psychometric analysis of 2025 operational tests | May-June 2025
Conduct rangefinding with NYS educators for scoring 2025 Writing field tests | June-July 2025
Deliver general research file to NYSED for 2025 operational tests | June-July 2025
Conduct Passage and Item review meeting with NYS educators for 2026 stand alone field tests | June-July 2025
Score 2025 NYSESLAT field tests (MC and CR items) | 2025-07-01
Conduct rescoring of 10% of locally scored 2025 operational test writing responses | Aug-Sept 2025
Provide technical report on 2025 stand alone field tests | Sept-25
Provide technical report on 2025 operational tests | 2025-10-01
TOTAL YEAR 2 |  | 0

## Year 4 (hidden)
CONTRACT YEAR BUDGET AMOUNT $ VID # | MONTH / YEAR | TOTAL COST | INVOICE NUMBER | INVOICE DATE | INVOICE AMOUNT | PAID DATE | CHECK NUMBER | PAID AMOUNT | NOTES | Cost Center # | Price Reduction | Price Difference | Late Fee
TOTALS YEAR |  | BUDGET |  |  | INVOICED |  |  | PAID
CONTRACT TOTAL YEAR
CONTRACT PAID YEAR
BALANCE LEFT ON CONTRACT FOR YEAR

## Year 5 (hidden)
CONTRACT YEAR BUDGET AMOUNT $ VID # | MONTH / YEAR | TOTAL COST | INVOICE NUMBER | INVOICE DATE | INVOICE AMOUNT | PAID DATE | CHECK NUMBER | PAID AMOUNT | NOTES | Cost Center # | Price Reduction | Price Difference | Late Fee
TOTALS YEAR |  | BUDGET |  |  | INVOICED |  |  | PAID
CONTRACT TOTAL YEAR
CONTRACT PAID YEAR
BALANCE LEFT ON CONTRACT FOR YEAR

## Budget Summary
Budget Form – Cost Proposal
New York State Education Department
Request for Proposals 23-015
Elementary, Intermediate (Middle) Level, and High School New York State English as a Second Language Achievement Test (NYSESLAT)
Bidder Name:
YEAR 1 | YEAR 2 | GRAND TOTAL
0 | 0 | 0
The Financial Criteria portion of the RFP will be scored based upon the grand total cost.
Bidders should be prepared to show how they derived the amounts for each activity should they be subject to audit by NYSED or Office of the State Comptroller.
Bidder Signature: |  | Date:
Printed Name:
Company Name:
Company Address:

## Subcontracting
Request for Proposals 23-015
Elementary, Intermediate (Middle) Level, and High School New York State English as a Second Language Achievement Test (NYSESLAT)
Subcontracting Form
Bidder Name:
Name of Subcontractor | M/WBE* | Entity Type | Work Description | Year 1 Cost | Multi-Year Cost (including Year 1)
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
| ¨ MBE | ¨ For Profit
| ¨ WBE | ¨ Not –For-Profit
|  |  |  | Total Multi-Year Subcontracting Costs | 0
|  |  |  | Total Multi-Year Project Budget | 0
|  |  |  | Total Multi-Year Subcontracting Costs divided by Total Multi-Year Budget (%)** | #DIV/0!
*Indicate whether the subcontractor is a Minority or Women–Owned Business Enterprise.
Leave box blank if subcontractor is neither.
**Subcontracting is limited to thirty percent (30%) of the total contract budget.

## MWBE
Request for Proposals 23-015
Elementary, Intermediate (Middle) Level, and High School New York State English as a Second Language Achievement Test (NYSESLAT)
MWBE Purchases Form
Bidder Name:
Table 1: Minority Business Enterprise (MBE)
Name of Vendor | Type of Services or Supplies | Year 1 Cost | Multi-Year Cost (including Year 1)
|  | Total MBE Costs | 0
|  | Total Budget | 0
|  | Total MBE Costs divided by Total Budget (%) | #DIV/0!
Table 2: Women-Owned Business Enterprise (WBE)
Name of Vendor | Type of Services or Supplies | Year 1 Cost | Multi-Year Cost (including Year 1)
|  | Total WBE Costs | 0
|  | Total Budget | 0
|  | Total WBE Costs divided by Total Budget (%) | #DIV/0!

## Budget (hidden)
Encumbered
Contract Year |  | TOTAL
1
2
3
4
5
Invoices
Contract Year |  | TOTAL
1
2
3
4
5
Paid
Contract Year |  | TOTAL
1
2
3
4
5