## Slide 1
Presented by
Ryan Garrison, Director of Technology
Smart Schools Bond Act
HUNT Engineers, Architects, Land Surveyors, P.C.
Investment Plan Preliminary Approval
Notes: Jeff

## Slide 2: Project Phasing
District Wide Technology & Security System Improvements |  |  |  |  |  |  |  |  |  |  | December 18th , 2014 |  | 
 |  |  | Total Construction Cost |  |  | Total OGS |  | 5% Design Contingency | 2% Inflation Per Year | 10% Construction Contingency | 20% Incidentals | Total Project Cost | 
Phase 1 (Smart Schools Bond Act) |  | HS Data Rooms, Cabling, Wireless & Security 1. All High School Closets 2. Recabling, Cable tray, Ceilings & Lighting. 3. Wireless network. 4. Security cabling & cameras. 5. Network Switches OGS | $1,737,700 |  |  | $308,000 |  | $102,285 | $42,960 | $219,094 | $482,008 | $2,892,047 | 
Phase 2 (Public Referendum May 19th, 2015) |  | MS Data Rooms, Cabling, Wireless & Security 1. All Middle School Closets 2. Recabling, Cable tray, Ceilings & Lighting. 3. Wireless network. 4. Security cabling & cameras. 5. Network Switches OGS | $1,349,200 |  |  | $320,000 |  | $83,460 | $70,106 | $182,277 | $401,009 | $2,406,052 | 
Phase 3 (Future Public Referendum) |  | Elementary Data Rooms 1. All elementary School Closets 2. Recabling, Cable tray, Ceilings & Lighting where Closets are being relocated. 3. Wireless where Closets are where data room is being relocated. 4. Security cabling in zones where data room is being relocated. 5. Network Switches | $875,103 |  |  | $503,000 |  | $68,905 | $86,820 | $153,383 | $337,442 | $2,024,653 | 
Phase 4 (Future Public Referendum) |  | Elementary Cabling (Classroom, Wireless, Security) 1. Elementary Classroom & Office Cabling (Minus Phase 1 Cabling). 2. Elementary Wireless Cabling (Minus Phase 1 Cabling). 3. Elementary Security Cabling (Minus Phase 1 Cabling). 4. Elementary Ceilings, Lights & Cable Tray (Minus work in Phase 1) 5. Wireless & Security OGS | $1,320,500 |  |  | $391,000 |  | $85,575 | $143,766 | $194,084 | $426,985 | $2,561,910 | 
Phase 5 (Future Public Referendum) |  | VoIP & IP Video 1. Voice over IP Phone System 2. IP Video Distribution |  |  |  | $888,500 |  | $44,425 | $74,634 | $100,756 | $221,663 | $1,329,978 | 
Totals |  |  | $5,282,503 |  |  | $2,410,500 |  | $384,650 | $418,287 | $849,594 | $1,869,107 | $11,214,640 | 
 |  | Total Construction & OGS |  |  |  | $7,693,003 |  |  |  |  |  |  | 

## Slide 3: High School Scope Items
Renovate High School Data Rooms
Re-cable data cabling with proper pathways
Wireless Network Upgrade
Security Camera Upgrade
Network Switch Upgrades

## Slide 4: Investment Plan Requirements
Approved Instructional Technology Plan
Consult with stakeholders
Consult with non-publics
SED Preliminary Scope Review
Preliminary SSIP Approval by BoE
Post to website for 30 days and receive comments
Public hearing
Final SSIP Approval by BoE
Submit to SED for review

## Slide 5: Stakeholder Involvement
Required by SED for the investment plan submission.
Scope was presented to the district’s Implementation Team in June and September.
The committee included staff, teachers, students and community members.

## Slide 6
School Connectivity
Community Connectivity
Classroom Technology
Pre-K Classrooms
Mobile Classroom Replacement
High Tech Security
Allowable Categories

## Slide 7
Investment Plan Overview
Category | Sub-Allocations
School Connectivity | $2,841,966
Community Connectivity | -
Classroom Technology | -
Pre-K Classrooms | -
Replace Mobile Classrooms | -
High Tech Security | $87,896
Totals | $2,929,862

## Slide 8
School Connectivity
Category | Sub-Allocations
Network/Access Costs | -
Outside Plant Costs | -
School Internal Connections & Components | $2,841,966
Professional Services | -
Testing | -
Other Costs | -
Totals | $2,841,966

## Slide 9
High Tech Security
Category | Sub-Allocations
Capital-Intensive Security Project (Standard Review) | $87,896
Main Entrance Electronic Security System (Streamlined Review) | -
Main Entrance Entry Control System (Streamlined Review) | -
Approved Door Hardening Project (Streamlined Review) | -
Other Costs | -
Totals | $87,896

## Slide 10
Approval of Preliminary SSBA Investment Plan by BoE (10/29)
Post plan to district website for 30 days (10/30)
Public Hearing (12/17)
Approval of Finalized Investment Plan (12/17)
Submission of Finalized Investment Plan (12/18)
Next Steps…

## Slide 11: Questions?